## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-01 | Setup of project environment (JDK,Spring,DB) | MUST HAVE |  | Bishwanath Kumam | 3- Completed
S1 | S1 | US-02 | Implement Task CRUD using Thymeleaf UI | MUST HAVE | US-01 | Bishwanath Kumam | 3- Completed
S1 | S1 | US-03 | Add filters,sorting & pagination in UI | MUST HAVE | US-02 | Bishwanath Kumam | 3- Completed
S1 | S1 | US-04 | Add enums(Status ,Priority)+UI improvements | MUST HAVE | US-02 | Bishwanath Kumam | 3- Completed
S2 | S2 | US-01 | Implement REST APIs for Task CRUD | SHOULD HAVE |  | Bishwanath Kumam | 3- Completed
S2 | S2 | US-02 | Add REST filtering ,sorting & pagination | MUST HAVE |  | Bishwanath Kumam | 3- Completed
S2 | S2 | US-03 | API testing via Postman +final cleanup |  |  | Bishwanath Kumam | 3- Completed
S3 | S3 | US-01 | User registration using email and password ,including storing user details in the database | MUST HAVE |  | Bishwanath Kumam | 3- Completed
S3 | S3 | US-02 | Generate and send OTP to the user's email and verify the OTP to activate the account | MUST HAVE |  | Bishwanath Kumam | 3- Completed
S3 | S3 | US-03 | User Login functionality using email and password,validating credentials against the database | MUST HAVE |  | Bishwanath Kumam | 3- Completed
S3 | S3 | US-04 | Maintain authenticated user session to ensure only logged-in users can access their own tasks. | MUST HAVE |  | Bishwanath Kumam | 3- Completed
S4 | S4 | US-01 | Implement task completion tracking & insights | MUST HAVE |  | Bishwanath Kumam | 3- Completed
S4 | S4 | US-02 | Build dashboard with visual analytics | MUST HAVE |  | Bishwanath Kumam | 3- Completed
S4 | S4 | US-03 | Add user profile & secure password management | MUST HAVE |  | Bishwanath Kumam | 3- Completed
S4 | S4 | US-04 | Multi language support & full deployment | MUST HAVE |  | Bishwanath Kumam | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T-1 | Downloading Intellij IDE with java 17 jdk | 2025-11-27 | 2025-11-29 |  | Others | 3- Completed
US-01 | T-2 | Downloading spring project initializer zip file from start.spring.io | 2025-12-27 | 2025-12-29 |  | Others | 3- Completed
US-02 | T-1 | Creating get and post tasks api | 2025-12-01 | 2025-12-02 |  | Coding | 3- Completed
US-02 | T-2 | Creating delete and update api | 2025-12-01 | 2025-12-03 |  | Coding | 3- Completed
US-02 | T-3 | Add validation and start implementing css | 2025-12-04 | 2025-12-05 |  | Coding | 3- Completed
US-02 | T-4 | Mysql DB connection with the api. | 2025-12-05 | 2025-12-06 |  | Coding | 3- Completed
US-03 | T-1 | Add paging,filter and search logic in service class | 2025-12-10 | 2025-12-11 |  | Coding | 3-Completed
US-03 | T-2 | Adding ui code for paging ,filter and serch in thymeleaf | 2025-12-10 | 2025-12-13 |  | Coding | 3-Completed
US-04 | T-1 | Creating enum class for status and priority and replace for String in logic | 2025-12-15 | 2025-12-16 |  | Coding | 3-Completed
US-01 | T-1 | Implement REST APIs for Task CRUD and add view task | 2025-12-16 | 2025-12-17 |  | Coding | 3-Completed
US-02 | T-1 | Add Rest filtering ,paging and sorting and implement ignore case in searching and filtering | 2025-12-17 | 2025-12-18 |  | Coding | 3-Completed
US-03 | T-1 | API testing via Postman +final cleanup | 2025-12-18 | 2025-12-19 |  | Coding | 3-Completed
US-03 | T-2 | Creating Junit test functions and testing | 2025-12-19 | 2025-12-23 |  | Unit Testing | 3-Completed
US-03 | T-3 | API for pending tasks for today,tasks for 2 days or 5days and overdue tasks | 2025-12-23 | 2025-12-24 |  | Coding | 3-Completed
US-03 | T-4 | Implement Swagger Ui for api documentation | 2025-12-24 | 2025-12-24 |  | Coding | 3-Completed
US-01 | T-1 | User registration using email and password ,including storing user details in the database | 2025-12-29 | 2025-12-30 |  | Coding | 3-Completed
US-02 | T-1 | Generate and send OTP to the user's email and verify the OTP to activate the account | 2025-12-30 | 2026-01-02 |  | Coding | 3-Completed
US-03 | T-1 | User Login functionality using email and password,validating credentials against the database | 2025-12-30 | 2026-01-04 |  | Coding | 3-Completed
US-04 | T-1 | Maintain authenticated user session to ensure only logged-in users can access their own tasks. | 2025-12-05 | 2026-01-08 |  | Coding | 3-Completed
US-01 | T-1 | Implement tasks for each user,using one to many relationship | 2026-01-08 | 2026-01-09 |  | Coding | 3-Completed
US-01 | T-2 | Add email notification as reminder for pending tasks using email,create api endpoint for finding completed tasks,due tasks ,due today tasks | 2026-01-09 | 2026-01-12 |  | Coding | 3-Completed
US-02 | T-1 | Build dashboard with visual analytics | 2026-01-09 | 2026-01-10 |  | Coding | 3-Completed
US-03 | T-1 | Implement secure password management using bcrypt | 2026-01-13 | 2026-01-15 |  | Coding | 3-Completed
US-03 | T-2 | Add user profile ,upload profile ,delete profile | 2026-01-13 | 2026-01-15 |  | Coding | 3-Completed
US-03 | T-3 | Add tasks downloadable as csv or send via email | 2026-01-19 | 2026-01-20 |  | Coding | 3-Completed
US-04 | T-1 | Multi language support & full deployment | 2026-01-20 | 2026-01-27 |  | Coding | 3-Completed

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-11-27 | 2026-12-10 | Bishwanath Kumam | 2025-11-27 | 2025-12-16 |  | Completed
2 | 2 | 2025-12-11 | 2025-12-24 | Bishwanath Kumam | 2025-12-24 | 2025-12-24 |  | Completed
3 | 3 | 2025-12-26 | 2026-01-09 | Bishwanath Kumam | 2025-12-30 | 2026-01-09 |  | Completed
4 | 4 | 2026-01-13 | 2026-01-27 | Bishwanath Kumam | 2026-01-13 | 2026-01-27 |  | Completed
5
6
7